## 12-Week Tracker
Week | Focus | Planned task | Completion evidence | Status | Target / completion date | Planned hours | Actual hours | Resource link | Evidence / project link | Notes | Summary
1 | Spreadsheet foundations | Inspect a small public sales dataset; note fields and data-quality issues. | Clean table, consistent headers/types, 4 working formulas, short data dictionary. | Completed | 2026-10-17 | 6 |  | Google Sheets or Excel; Microsoft PivotTable guide |  |  | Completion rate
2 | Spreadsheet analysis | Build a region/product summary and answer 3 questions; reconcile totals. | One pivot, 2 labelled charts, 3 evidence-based answers; record source/licence. | In Progress | 2026-10-24 | 6 |  | Google Sheets help; Microsoft PivotTable guide |  |  | Planned hours
3 | SQL foundations | Translate 5 spreadsheet questions into SQL; complete introductory exercises. | At least 8 correct single-table queries saved with question/result notes. | Not Started | 2026-10-27 | 6 |  | SQLBolt Lessons 1–5 |  |  | Actual hours
4 | SQL aggregation and joins | Answer questions spanning related tables. | At least 5 queries including join and grouped result; reconcile one total. | Not Started |  | 6 |  | SQLBolt Lessons 6–12/topics; Kaggle Intro to SQL |  |  | Status counts
5 | SQL for reusable analysis | Create multi-step CTE with CASE categories and export a result table. | Runnable CTE + CASE query and CSV; note SQL dialect/adaptations. | Not Started |  | 6 |  | Kaggle Intro to SQL; SQLBolt intermediate topics |  |  |  | Completed
6 | Python and Pandas start | Load Week 5 CSV and produce a grouped summary. | Notebook runs top-to-bottom; row count and grouped totals checked. | Not Started |  | 6 |  | Kaggle Intro to Programming/Python; Pandas tutorials |  |  |  | In Progress
7 | Cleaning and exploratory analysis | Clean selected dataset; log changes, reasons, impact; keep raw source distinct. | Reproducible steps, before/after row counts, explained nulls, 3 findings. | Not Started |  | 6 |  | Kaggle Data Cleaning; Pandas tutorials |  |  |  | Not Started
8 | Statistics for analysts | Summarize cleaned data; explain one limitation and correlation ≠ causation. | Plain-language note with 5 statistics and 3 interpretations. | Not Started |  | 6 |  | Khan Academy Statistics; Pandas docs |  |  |  | Needs Review
9 | Visual storytelling | Create charts for project questions; write a takeaway for each. | 4 readable charts with labels and evidence-based takeaways. | Not Started |  | 6 |  | Matplotlib; Seaborn; Kaggle Data Visualization
10 | Dashboard and QA | Build interactive or spreadsheet dashboard; verify KPIs against SQL/Pandas. | 3 KPIs, one useful filter and validation notes; Tableau/Sheets alternative. | Not Started |  | 6 |  | Tableau Public; Microsoft Learn Power BI training
11 | Portfolio assembly | Assemble project; request peer review if available. | Repository/folder has source attribution, SQL, notebook, visuals and README draft. | Not Started |  | 6 |  | GitHub Guides; GitHub Free; Kaggle Datasets
12 | Review and presentation | Re-run from clean start; address review feedback; record 3–5 minute demo. | Reproducible project, final README, limitations, recommendations, demo. | Not Started |  | 6 |  | GitHub; chosen dashboard tool